## Sheet1
Type of Task | Project Activity ID | Activity ID | Task | Hours Alloted Per Task | Men Per Day | Days | Task Start | Task End
Electrical | 7 | 7 | Mobilize - deliver materials, equipment and set ATS | 16 | 2 | 1 | Tue 9/2/14 | Tue 9/2/14
Electrical | 8 | 8 | Install overhead conduit from building entry pullbox to ATS | 48 | 2 | 3 | Wed 9/3/14 | Fri 9/5/14
Electrical | 10 | 10 | Install overhead conduit from ATS to pullbox at switchgear & install conduit to sub panel | 48 | 2 | 3 | Wed 9/10/14 | Fri 9/12/14
Construction | 11 | 11 | Layout walls, bollards and saw cut curb and bollard openings | 16 | 2 | 1 | Tue 9/2/14 | Tue 9/2/14
Construction | 12 | 12 | Demo grass area and excavate/remove dirt | 32 | 2 | 2 | Wed 9/3/14 | Thu 9/4/14
Construction | 13 | 13 | Excavate trench for underground electric | 16 | 2 | 1 | Fri 9/5/14 | Fri 9/5/14
Construction | 14 | 14 | Layout and form conduit opening at generator | 8 | 2 | 0.5 | Mon 9/8/14 | Mon 9/8/14
Construction | 15 | 15 | Reroute and repair sprinkler lines | 8 | 2 | 0.5 | Mon 9/8/14 | Mon 9/8/14
Electrical | 16 | 16 | Install underground electric | 32 | 2 | 2 | Mon 9/8/14 | Tue 9/9/14
Construction | 17 | 17 | Backfill and compact electrical trench | 16 | 2 | 1 | Wed 9/10/14 | Wed 9/10/14
Construction | 19 | 19 | Finish grade, form generator pad and dig bollard holes | 16 | 2 | 1 | Thu 9/11/14 | Thu 9/11/14
Construction | 20 | 20 | Install rebar for generator pad and retaining wall | 32 | 2 | 2 | Fri 9/12/14 | Mon 9/15/14
Electrical | 21 | 21 | Install grounding system | 8 | 2 | 0.5 | Mon 9/15/14 | Mon 9/15/14
Construction | 22 | 22 | Pour concrete | 8 | 2 | 0.5 | Tue 9/16/14 | Tue 9/16/14
Construction | 23 | 23 | Remove form boards | 8 | 2 | 0.5 | Wed 9/17/14 | Wed 9/17/14
Construction | 24 | 24 | Install masonry walls and grout | 48 | 2 | 3 | Wed 9/17/14 | Mon 9/22/14
Construction | 25 | 25 | Water proof, backfill & compact walls | 32 | 2 | 2 | Mon 9/22/14 | Thu 9/25/14
Electrical | 26 | 26 | Install overhead conduit system for remote annunciator | 16 | 2 | 1 | Mon 9/15/14 | Tue 9/16/14
Electrical | 27 | 27 | Pull wire from generator to ATS, ATS to pull box at switchgear | 32 | 4 | 1 | Tue 9/16/14 | Wed 9/17/14
Electrical | 28 | 28 | Set generator, anchor and terminate wiring at gen and ATS | 16 | 2 | 1 | Thu 9/18/14 | Thu 9/18/14
Electrical | 30 | 30 | POWER OUTAGE: Break bus and terminate wiring in switchgear | 12 | 3 | 0.5 | Fri 9/19/14 | Fri 9/19/14
Electrical | 31 | 31 | Demobilize and site clean-up | 16 | 2 | 1 | Mon 9/22/14 | Tue 9/23/14
Electrical | 33 | 33 | POWER OUTAGE: Start-up, Test, Training and simulate power outage | 8 | 2 | 0.5 | Tue 9/23/14 | Tue 9/23/14
Electrical | 34 | 34 | Project Close-out and Complete Punch List | 8 | 1 | 1 | Fri 9/26/14 | Fri 9/26/14
|  |  | Totals | 500 |  | 30.5