## Sheet1
| Period From: |  | 2014-09-01 |  | To: | 2014-09-21 | [9 empty] | PROJECT NAME: GPG_pro | [37 empty] | Period From: |  | 2014-09-22 |  | To: | 2014-09-28 | [9 empty] | PROJECT NAME: GPG_pro
| GPG #: |  | 5114 | [12 empty] | SHORT INTERVAL SCHEDULE | [37 empty] | GPG #: |  | 5114 | [12 empty] | SHORT INTERVAL SCHEDULE
Approx. 2 man days | Activity ID | Est. Hours | Actual Hours | Description |  |  |  | Week | 1st WEEK ESTIMATED | [6 empty] | 1st WEEK ACTUAL | [6 empty] | 2nd WEEK ESTIMATED | [6 empty] | % Complete | 2nd WEEK ACTUAL | [6 empty] | 3rd WEEK ESTIMATED | [6 empty] | % Complete | 3rd WEEK ACTUAL | [6 empty] | % Complete | Activity ID | Est. Hours | Actual Hours | Description |  |  |  | Week | 4th WEEK ESTIMATED | [6 empty] | 4th WEEK ACTUAL | [6 empty] | 5th WEEK ESTIMATED | [6 empty] | % Complete | 5th WEEK ACTUAL | [6 empty] | 6th WEEK ESTIMATED | [6 empty] | % Complete | 6th WEEK ACTUAL | [6 empty] | % Complete
[8 empty] | Date | 9/1 | 9/2 | 9/3 | 9/4 | 9/5 | 9/5 | 9/7 | 9/1 | 9/2 | 9/3 | 9/4 | 9/5 | 9/5 | 9/7 | 9/8 | 9/9 | 9/10 | 9/11 | 9/12 | 9/13 | 9/14 |  | 9/8 | 9/9 | 9/10 | 9/11 | 9/12 | 9/13 | 9/14 | 9/15 | 9/16 | 9/17 | 9/18 | 9/19 | 9/20 | 9/21 |  | 9/15 | 9/16 | 9/17 | 9/18 | 9/19 | 9/20 | 9/21 | [8 empty] | Date | 9/22 | 9/23 | 2/24 | 9/25 | 9/26 | 9/27 | 9/28
[8 empty] | Day | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | [8 empty] | Day | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S
2 | 7 | 16 | x | Mobilize - deliver materials, equipment and set ATS |  |  |  | M: off; T: 16 | [24 empty] | 7 | 16 | x | Mobilize - deliver materials, equipment and set ATS
3 | 8 | 48 | x | Install overhead conduit from building entry pullbox to ATS |  |  |  | W: 16; T: 16; F: 16 | [24 empty] | 8 | 48 | x | Install overhead conduit from building entry pullbox to ATS
0 | 9 | 0 | x | MEETING: Order glass panel with holes for conduit entry into building |  |  |  | F: 0 | [24 empty] | 9 | 0 | x | MEETING: Order glass panel with holes for conduit entry into building
3 | 10 | 48 | x | Install overhead conduit from ATS to pullbox at switchgear and install conduit to sub panel |  |  |  | W: 16; T: 16; F: 16 | [24 empty] | 10 | 48 | x | Install overhead conduit from ATS to pullbox at switchgear and install conduit to sub panel
1 | 11 | 16 | x | Layout walls, bollards and saw cut curb and bollard openings |  |  |  | T: 16 | [24 empty] | 11 | 16 | x | Layout walls, bollards and saw cut curb and bollard openings
2 | 12 | 32 | x | Demo grass area and excavate/remove dirt |  |  |  | W: 16; T: 16 | [24 empty] | 12 | 32 | x | Demo grass area and excavate/remove dirt
1 | 13 | 16 | x | Excavate trench for underground electric |  |  |  | F: 16 | [24 empty] | 13 | 16 | x | Excavate trench for underground electric
0.5 | 14 | 8 | x | Layout and form conduit opening at generator |  |  |  | M: 8 | [24 empty] | 14 | 8 | x | Layout and form conduit opening at generator
0.5 | 15 | 8 | x | Reroute and repair sprinkler lines |  |  |  | M: 8; T: off site | [24 empty] | 15 | 8 | x | Reroute and repair sprinkler lines
2 | 16 | 32 | x | Install underground electric |  |  |  | M: 16; T: 16 | [24 empty] | 16 | 32 | x | Install underground electric
1 | 17 | 16 | x | Backfill and compact electrical trench |  |  |  | T: A; W: 16 | [24 empty] | 17 | 16 | x | Backfill and compact electrical trench
0 | 18 | 0 | x | Install glass panel |  |  |  | F: 0 | [24 empty] | 18 | 0 | x | Install glass panel
1 | 19 | 16 | x | Finish grade, form generator pad and dig bollard holes |  |  |  | T: 16 | [24 empty] | 19 | 16 | x | Finish grade, form generator pad and dig bollard holes
2 | 20 | 32 | x | Install rebar for generator pad and retaining wall |  |  |  | T: B; F: 16 | [8 empty] | 16 | [15 empty] | 20 | 32 | x | Install rebar for generator pad and retaining wall
0.5 | 21 | 8 | x | Install grounding system | [33 empty] | 8 | [15 empty] | 21 | 8 | x | Install grounding system
0.5 | 22 | 8 | x | Pour concrete | [33 empty] | C | 8 | [14 empty] | 22 | 8 | x | Pour concrete
0.5 | 23 | 8 | x | Remove form boards | [35 empty] | 8 | [13 empty] | 23 | 8 |  | Remove form boards
3 | 24 | 48 | x | Install masonry walls and grout | [35 empty] | 8 | 16 | 16 | [11 empty] | 24 | 48 |  | Install masonry walls and grout |  |  |  |  | 8
2 | 25 | 32 | x | Water proof, backfill & compact walls | [37 empty] | D | [11 empty] | 25 | 32 |  | Water proof, backfill & compact walls |  |  |  |  | 8 | 16 | 8
1 | 26 | 16 | x | Install overhead conduit system for remote annunciator | [33 empty] | 8 | 8 | [14 empty] | 26 | 16 |  | Install overhead conduit system for remote annunciator
4m, 1d | 27 | 32 | x | Pull wire from generator to ATS, ATS to pull box at switchgear | [34 empty] | 8 | 24 | [13 empty] | 27 | 32 |  | Pull wire from generator to ATS, ATS to pull box at switchgear
1 | 28 | 16 | x | Set generator, anchor and terminate wiring at gen and ATS | [36 empty] | 16 | [12 empty] | 28 | 16 |  | Set generator, anchor and terminate wiring at gen and ATS
2 | 29 | 0 |  | Install fence | [37 empty] | 0 | [11 empty] | 29 | 0 |  | Install fence
0.5 | 30 | 12 |  | POWER OUTAGE: break bus and terminate wiring in switchgear | [37 empty] | 12 | [11 empty] | 30 | 12 |  | POWER OUTAGE: break bus and terminate wiring in switchgear
1 | 31 | 16 |  | Demobilize and site clean-up | [49 empty] | 31 | 16 |  | Demobilize and site clean-up |  |  |  |  | 16
0 | 32 | 0 |  | Fuel generator, sync control wiring between gen & ATS | [49 empty] | 32 | 0 |  | Fuel generator, sync control wiring between gen & ATS
0.5 | 33 | 8 |  | POWER OUTAGE: Start-up, Test & Training | [49 empty] | 33 | 8 |  | POWER OUTAGE: Start-up, Test & Training |  |  |  |  | E | 8
1 | 34 | 8 |  | Project Close-out and Complete Punch List | [49 empty] | 34 | 8 |  | Project Close-out and Complete Punch List | [8 empty] | 8
| Notes: |  |  | SOME OF THE BOLLARDS ARE REMOVABLE AND WILL REQUIRE PVC SLEEVES | [49 empty] | Notes: |  |  | SOME OF THE BOLLARDS ARE REMOVABLE
| Remarks: |  |  | Order and deliver bollards, schedule meeting with glass contractor, fence contractor meeting when block work starts | [49 empty] | Remarks: |  |  | Order and deliver bollards, schedule meeting with glass contractor, fence contractor meeting when block work starts
| Equipment Needs: |  |  | Backhoe, bobcat, post hole auger (when needed), tamper, porta-potty, temporary fence for security, delineators and caution tape. MAKE SURE EQUIPMENT IS DELIVERED FULL OF FUEL! | [49 empty] | Equipment Needs: |  |  | Backhoe, bobcat, post hole auger (when needed), tamper, porta-potty, temporary fence for security, delineators and caution tape. MAKE SURE EQUIPMENT IS DELIVERED FULL OF FUEL!
[7 empty] | Sub Contractor | S: Electrical Crew; F: Inspections: |  |  | A: underground electric B: pad compaction C: rebar | [27 empty] | Sub Contractor | [7 empty] | Electrical Crew | [11 empty] | Inspections: |  |  |  |  | A: underground electric B: pad compaction C: rebar
[7 empty] | Meeting | S: Construction Crew |  |  | D: masonry wall (before grout) E: final electric | [27 empty] | Meeting | [7 empty] | Construction Crew | [16 empty] | D: masonry wall (before grout) E: final electric
|  | 500 |  | PROJECT TOTAL HOURS
|  | 502 |  | HOURS ALLOTTED IN BID